## List of points to include
Steps for project
Data Source | CSV dataset
Spark Transformations to include | .count()
| .map() |  |  |  |  | csv -> s3 | python+ boto
.reduce()
.filter()
.union()
.flatMap()
.reduceByKey()
.sortByKey()
countByKey()
Airflow steps list | Installation | postgres | metadata
| Dags | sqllite | Actual | step 1 | data checks
|  |  |  | step 2 | Transformation
|  |  |  | step 3 | loading

## Important Links
https://jacobcelestine.com/knowledge_repo/colab_and_pyspark/

## TimeLine
Tasks | Timeline
Load CSV data set | 25-28 Dec
Tranforming CSV data set using Pyspark | 28-14Jan
Schelure in Airflow | 15-21 jan
Load processed table into SQL db | 22-26 jan
Build report using Power BI | 27-30jan