## List of points to include
Steps for project
Data Source | CSV dataset
Spark Transformations to include | .count()
.map()
.reduce()
.filter()
.union()
.flatMap()
.reduceByKey()
.sortByKey()
countByKey()
Airflow steps list

## Important Links
https://jacobcelestine.com/knowledge_repo/colab_and_pyspark/

## TimeLine
Tasks | Timeline
Load CSV data set | 25-28 Dec
Tranforming CSV data set using Pyspark | 28-14Jan
Schelure in Airflow | 15-21 jan
Load processed table into SQL db | 22-26 jan
Build report using Power BI | 27-30jan